## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | 1 | python installation and Introduction of python | MUST HAVE | None | Emmadi Srikar | 3- Completed
S1 | S1 | 1 | Natural Language Processing(NLP) and Data Frame Practice | SHOULD HAVE | vs code | Emmadi Srikar | 3- Completed
S1 | S1 | 1 | Understanding the Project | SHOULD HAVE | None | Emmadi Srikar | 3- Completed
S1 | S1 | 1 | Agile Sheet form filling | MUST HAVE | None | Emmadi Srikar | 3- Completed
S2 | S2 | 2 | Assignments | MUST HAVE | USID-2 | Emmadi Srikar | 3- Completed
S1 | S1 | 1 | Learning Strong Fundamentals for doing Project | MUST HAVE | None | Emmadi Srikar | 3- Completed
S2 | S2 | 2 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | MUST HAVE | Python Environment setup | Emmadi Srikar | 3- Completed
S3 | S3 | 3 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | MUST HAVE | vs code | Emmadi Srikar | 3- Completed
S4 | S4 | 4 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | MUST HAVE | github,vs code | Emmadi Srikar | 3- Completed
Note on F1: ====== ID#AAABrLuDSeU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 |  | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Learning Strong Fundamentals for doing Project | 5th Sep | 19th sep | Emmadi Srikar | Leant and practiced the python concepts | Completed |  | installation | python intro | keywords | Data types | Diff Datatypes |  |  | Flowcontrol | Function Part-1 | Function part-2 | Modules |  | OOPS | Packages | control packages
2 | 1 | Establish infrastructure for ticket data integration & Pre-process Historical Ticket Data | 20th sep | 3rd Oct | Emmadi Srikar | learnt about NLP,pre-processing historical data and prepared the training input for LLM | Completed |  | NLP introduction | project understanding | Created service account and loading data from sheets | Service account and API | loading the dataset and milestone 1 introduction | discussed about dataframe,text preprocessing |  | Tokenization |  | lemmatization,stopword removal and code step by step explanation |  | About EDA |  | Feature Engineering | prepared training input for LLM
3 | 1 | Knowledge Categorization & Tagging Engine and Prompt Engineering & Automation Pipeline | 4th oct | 18th oct | Emmadi Srikar | learnt about tickets,category,tags,examples and prompt engineering and also practiced LLaMA3 model example hands on ,automation pipeline | Completed |  | Introduction of milestone 2 | revised the previous topics covered | Knowledge Categorization and Tagging Engine | Desingining the prompt for LLM and done process for creating API key | prompt engineering | Automation pipeline and few shot prompt | Confusion Matrix,Accuracy of Model,Validation | Discussion on project updates | Worked on Assignment 1 | Classification code with diff data | Discuss on Archietecture Flow | FIASS semantic search | Semantic search system workflow | Building a Real-time API | practiced till topics covered
4 | 1 | Bulding Realtime recommendation, gap analysis, sheduling alerts and deployment | 19th oct | 2nd Nov | Emmadi Srikar | learnt Realtime recommendation Introduction & System Architecture | Completed |  | Practiced | gained knowledge about prevoius topics | Real Time API | Content Gap Analysis | Monitoring,Alerts&Automation | stramlit framework, Dashboard creation | learnt streamlit | Practiced Streamlit | executed diff things about streamlit | Revised | Building Streamlit Dashboard | Slack Integration | Project Workflow | practiced total | Deployed project on Github
Note on D2: ====== ID#AAABrLuDSeI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABrLuDSd4 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABrLuDSeY Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABrLuDSeM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABrLuDSeQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABrLuDSeg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABrLuDSe4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABrLuDSek Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABrLuDSd8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABrLuDSew Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABrLuDSeA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABrLuDSeE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABrLuDSec Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABrLuDSeo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on V3: ====== ID#AAABrLuDSe8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on W3: ====== ID#AAABrLuDSe0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on X3: ====== ID#AAABrLuDSes Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
s1 | Day1 | python installation issues | Reinstalled python and configured VS Code sucessfully
S1 | Day9 | Agile sheet Format unclear | Discussed with mentor and completed sheet filling
s2 | day20 | Ticket data Integration errors | Fixed dataset format issues and reprocessed data

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 06-09-2025 | 19-09-2025 | Emmadi Srikar | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session by mentor to clarify project goals.
2
3
4
5
6
7